## Sheet1
Project Milestone Semester 1
| 29/09/2021 Week 1 | 06/10/2021 Week 2 | 13/10/2021 Week 3 | 20/10/2021 Week 4 | 03/11/2021 Week 5 | 10/11/2021 Week 6 | 17/11/2021 Week 7 | 24/11/2021 Week 8 | 29/11/2021 Week 9
Project Planning
Scope | Scope
Project Management
Timetable | Timetable
Quality check |  |  |  | Quality Check
Implementation tools
Gantt Chart |  | Gantt Chart
Linear Responsibility Chart |  | Linear Responsibility Chart
Use Case Requirements Specification
Game Theme | Game Theme
Game Description |  |  | Game Description
Use Case Diagram |  |  |  | Use Case Diagram
Flow Chart |  |  | Flow Chart
System Analysis
Class Diagram |  |  |  |  | Class Diagram
Sequence Diagram |  |  |  |  | Sequence Diagram
Draft Game Layout | [7 empty] | Game Layout
Interim Video Demo
Java classes description |  |  |  |  | Java classes description
Java methods description |  |  |  |  | Java methods description
Java class declaration | [5 empty] | Java Classes declaration
Java methods declaration | [6 empty] | Java Methods declaration